## Sheet1
System | Cost | Total Time | Work Time | Work
Frame | 3000 | 12 weeks | 8 | Researching/contacting shops, minor modifications, weldings mounts for shifter, drilling holes, rivets
Transaxle
new | 1000 | 3 weeks | 12 | Researching/contacting shops, installing, securing, testing
in-house rebuild | 200 | 8 weeks | 48 | Disassemble, inspect (show expert), analyze, clean, replace bad parts, reassemble, test, evaluate performance
Front Suspension | 1000 | 4 weeks | 16 | Researching, pondering, ordering, assembling, testing
Rear Suspension | 400 | 4 weeks | 12 | Researching, ordering, assembling, testing
Engine | 150 | 1 day | 8 | Installing w/ crane, testing, evaluate performance
Body | 0 | 2 weeks | 24 | Drilling (aligned) holes in frame, assembling, riveting, cleaning, patching
Wheels
new | 700 | 3 weeks | 10 | Researching, ordering, attaching wheels, Mr. Tire, testing, evaluate performance
junkyard | 50 | 1 week | 16 | Junkyarding, attaching wheels, Mr. Tire, testing, evaluate performance
Electrical | 0 | 2 weeks | 24 | Researching car circuits, designing/documenting, wiring, testing, debugging
Brakes
Drum only | 450 | 6 weeks | 60 | Ordering, cutting, bending, flaring, installing lines, cylinders and springs, bleeding, testing, evaluate performance
Hybrid | 600 | 8 weeks | 80 | Researching disc breaks, ordering, cutting, bending, flaring, installing lines, cylinders and springs, bleeding, testing, evaluate performance
Control | 500 | 8 weeks | 60 | Researching, ordering, routing lines, mounting/fitting, designing shift linkage, testing
Fuel | 100 | 4 weeks | 20 | Buy plastic gas tank, install, fit fuel lines, mount fuel pump, carburetor, adjust timings, test